## Questionnaire
SteelBrick CPQ - Scoping Inputs | [5 empty] | Corresponds to what SteelBrick configures (except otherwise noted) | Fill out this column |  |  | Clarify here
Ref | Project Management | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
PM1 | Type of Project | EE/MM | List |  | Mid Market | Enterprise / Mid Market |  | Mid Market
PM2 | Duration for Orientation | Week | Number |  | 1 | Number of weeks |  | 1
PM3 | Duration for UAT | Week | Number |  | 1 | Number of weeks |  | 1
PM4 | Duration for Post Go Live Support | Week | Number |  | 1 | Number of weeks |  | 1
PM5 | Build Hours per Week | Week | Number |  | 20 | Expected average build hours per week and per resource |  | 20
PM6 | Build resources (Implementation Consultants) | Resource | Number |  | 1 | Number of resources for build |  | 1
PM7 | Additional Build Weeks (e.g. waiting for client activities) |  |  |  | 0 | Number of weeks |  | 0
Ref | Installation | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
A1 | User Profile security setup | Profile | Number |  | 0 | Number of profiles |  | 0
Ref | Product Catalog | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
B1 | Total number of products in catalog | Product | Number | Required | 0 | Enter 0 if customer handles the entire catalog |  | 0
B2 | Products configured by SB | Product | Number | Required | 0 | Products to be configured by SteelBrick |  | 0
B3 | Products configured by client and reviewed by SB | Product | Number | Required | 0 | Products reviewed by SteelBrick |  | 0
Ref | Bundles | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
C1 | Bundles configured by SB | Bundle | Number | Required | 0 | Number of bundles |  | 0
C2 | Bundles configured by Customer with SB assistance | Bundle | Number | Required | 0 | Number of bundles |  | 0
C3 | Features (configured by SB) | Feature | Number | Required if C1>0 or C2>0 | 0 | Number of Product Features (across all bundles) |  | 0
C4 | Options (configured by SB) | Option | Number | Required if C1>0 or C2>0 | 0 | Number of Product Options (across all bundles) |  | 0
C5 | Simple dependencies | Option Constraint | Number |  | 0 | Option Contraints |  | 0
C6 | Complex dependencies | Product Rule | Number |  | 0 | Product Validation Rules |  | 0
C7 | Automatic option selections | Product Rule | Number |  | 0 | Product Selection Rules |  | 0
C8 | Prior purchase constraints | Product Rule | Number |  | 0 | Number of rules involving prior purchases |  | 0
C9 | Configuration Attributes | Configuration Attribute | Number |  | 0 | Number of Product Configuration (across all bundles) |  | 0
Ref | Guided Selling | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
D1 | Quote Processes | Process | Number |  | 0 | Number of Guided Selling Processes |  | 0
D2 | Process Inputs (for all processes) | Input | Number | Required if D1>0 | 0 | Number of Process Inputs |  | 0
Ref | Custom Actions | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
E1 | Custom Actions | Action | Number |  | 0 | Number of Custom Actions |  | 0
E2 | Simple search filters | Filter | Number | Required if E1>0 | 0 | Search filters without dynamic source fields |  | 0
E3 | Complex search filters | Filter | Number |  | 0 | Search filters with dynamic source fields |  | 0
Ref | Pricing | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
F1 | Discount Schedules | Schedule | Number |  | 0 | Number of discount schedules |  | 0
F2 | Discount Tiers (for all schedules) | Tier | Number | Required if F1>0 | 0 | Number of tiers for all schedules |  | 0
F3 | Block Prices Tiers | Tier | Number |  | 0 | Number of block price tiers |  | 0
F4 | Price Rules | Rule | Number |  | 0 | Number of price rules |  | 0
F5 | Contracted Prices | Contracted Price | Number |  | 0 | Number of contracted prices |  | 0
F6 | Price Books | Data Loader Batch | Number |  | 0 | # of price books x # of currencies (Data Loader) |  | 0
F7 | Multi-Dimensional Quoting | Price Dimension | Number |  | 0 | Number of price dimensions |  | 0
F8 | Import Lines via CSV | Import Format | Number |  | 0 | Number of import formats (assumes up to 10 fields) |  | 0
Ref | Document Output - Template 1 | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
G1 | Number of Pages | Page | Number |  | 0 | If zero, no such template |  | 0
G2 | Number of Sections | Section | Number |  | 3 |  |  | 0
G3 | Number of Columns for line items (total) | Column | Number |  | 6 | Columns for all line item sections |  | 0
G4 | T&Cs - Static without merge fields |  | Boolean |  | TRUE | Terms field on the Quote Template will be used |  | TRUE
G5 | T&Cs - Static with merge fields | Page | Number |  | 0 | Number of pages of static text |  | 0
G6 | T&Cs - Static - Number of columns for text | Column | Number |  | 1 | Applies to Static with merge fields only |  | 0
G7 | T&Cs - Quote Terms | Term | Number |  | 0 | Assumed up to 2 conditions per term |  | 0
G8 | Custom Grouping |  | Boolean |  | FALSE | When grouping requires a formula |  | FALSE
G9 | Custom Rollups |  | Boolean |  | FALSE | When rollup requires a formula |  | FALSE
G10 | Conditional Sections | Section | Number |  | 0 | When condition requires a formula |  | 0
G11 | Conditional Line Columns | Column | Number |  | 0 | When condition requires a formula |  | 0
G12 | Filtered Line Items | Section | Number |  | 0 | When filtering requires a formula |  | 0
G13 | Strict Branding Guidelines |  | Boolean |  | FALSE |  |  | FALSE
G14 | Rich Graphics |  | Boolean |  | FALSE |  |  | FALSE
Ref | Document Output - Template 2 | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
H1 | Number of Pages | Page | Number |  | 0 | If zero, no such template |  | 0
H2 | Number of Sections | Section | Number |  | 3 |  |  | 0
H3 | Number of Columns for line items (total) | Column | Number |  | 6 | Columns for all line item sections |  | 0
H4 | T&Cs - Static without merge fields |  | Boolean |  | TRUE | Terms field on the Quote Template will be used |  | TRUE
H5 | T&Cs - Static with merge fields | Page | Number |  | 0 | Terms in an HTML Template Content |  | 0
H6 | T&Cs - Static - Number of columns for text | Column | Number |  | 1 | Applies to Static with merge fields only |  | 0
H7 | T&Cs - Quote Terms | Term | Number |  | 0 | Number of quote terms |  | 0
H8 | Custom Grouping |  | Boolean |  | FALSE | When grouping requires a formula |  | FALSE
H9 | Custom Rollups |  | Boolean |  | FALSE | When rollup requires a formula |  | FALSE
H10 | Conditional Sections | Section | Number |  | 0 | When condition requires a formula |  | 0
H11 | Conditional Line Columns | Column | Number |  | 0 | When condition requires a formula |  | 0
H12 | Filtered Line Items | Section | Number |  | 0 | When filtering requires a formula |  | 0
H13 | Strict Branding Guidelines |  | Boolean |  | FALSE |  |  | FALSE
H14 | Rich Graphics |  | Boolean |  | FALSE |  |  | FALSE
Ref | e-Signature | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
I1 | DocuSign |  | Boolean |  | FALSE | If SB installs and configure the package |  | FALSE
I2 | EchoSign |  | Boolean |  | FALSE | If SB installs and configure the package |  | FALSE
I3 | Fields to capture | Tag | Number |  | 0 | Tags to create
Ref | Native SFDC Approvals | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
J1 | Auto-approval |  | Boolean |  | FALSE | If customers wants quote to be auto-approved |  | FALSE
J2 | Approval Processes | Process | Number |  | 0 | Processes in addition to auto-approval process |  | 0
J3 | Single Reason Processes - Number of thresholds/Tiers | Step | Number |  | 0 | When a single reason is required (e.g. Discount) |  | 0
J4 | Multiple Reasons Processes - Number of steps including all tiers | Step | Number |  | 0 | When there are multiple approval reasons |  | 0
J5 | Email templates | Template | Number |  | 0 | Typically 4 templates |  | 0
Ref | SB Advanced Approvals | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
K1 | Approval Rules | Rule | Number |  | 0 | Number of rules |  | 0
K2 | Approval chains | Chain | Number |  | 0 | Number of chains |  | 0
K3 | Approvers | Approver | Number |  | 0 | Number of approvers |  | 0
K4 | Email templates | Template | Number |  | 0 | Typically 4 templates |  | 0
K5 | Parallel rules |  | Boolean |  | FALSE |  |  | FALSE
Ref | Renewals | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
L1 | Standard renewals |  | Boolean |  | FALSE |  |  | FALSE
L2 | Contract Amendments |  | Boolean |  | FALSE |  |  | FALSE
Ref | Deployment | UOM | Data Type | Constraints | Default value | Notes/Instructions | Your Response | Calculated Value | Validation | Comments
M1 | Type |  | Picklist | None ¦ Partial ¦ Full | None | Partial = no migration of products/bundles data |  | None
M2 | Migration Tool License? |  | Boolean |  | FALSE |  |  | FALSE

## Details
SteelBrick CPQ - Scoping Worksheet
Assumptions |  |  |  | Assumptions (Minutes) |  |  | Comments | Minutes |  |  |  | Hours |  |  |  | Rounded Hours
Project Management | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override) | PM | Architect | Consultant | Total | PM | Architect | Consultant | Total | PM | Architect | Consultant | Total
Number of Weeks | Includes weeks from kick-off until post go-live support completed | Week | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Project preparation | Kimble setup - Review documentation | Once | 1 | 120 | 60 | 60 |  | 120 | 60 | 60 | 240 | 2 | 1 | 1 | 4 | 2 | 1 | 1 | 4
Hand-off SOW Owner to Project Team |  | Once | 1 | 60 | 60 | 60 |  | 60 | 60 | 60 | 180 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3
Kick-off meeting/call |  | Once | 1 | 60 | 60 | 60 |  | 60 | 60 | 60 | 180 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3
Project tracking (status meeting + report) | 2 hours per week | Week | 1 | 120 | 15 | 15 |  | 360 | 45 | 45 | 450 | 6 | 0.75 | 0.75 | 7.5 | 6 | 1 | 1 | 8
Project tracking (steering committee) | One every 2 weeks | Week | 2 | 120 | 15 |  |  | 180 | 22.5 | 0 | 202.5 | 3 | 0.375 | 0 | 3.375 | 3 | 1 | 0 | 4
Coordinate activities | Base of 2 hours per week | Week | 1 | 120 | 30 | 30 |  | 360 | 90 | 90 | 540 | 6 | 1.5 | 1.5 | 9 | 6 | 2 | 2 | 10
Additional activities for Enterprise projects | 1 hour per 25 hours of build | Week | 25 | 60 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installation and Setup | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Package Installation |  | Each | 1 |  |  | 60 |  | 0 | 0 | 60 | 60 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
Profile Security |  | Profile | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Page layouts |  | Once | 1 |  |  | 60 |  | 0 | 0 | 60 | 60 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
Knowledge Transfer to Customer | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Profile Security Template |  | Once | 1 |  |  | 30 |  | 0 | 0 | 30 | 30 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 1 | 1
Data Prep Workbook |  | Once | 1 |  |  | 60 |  | 0 | 0 | 60 | 60 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
Product Master Data Collection |  | Once | 1 |  |  | 60 |  | 0 | 0 | 60 | 60 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
Pricing Master Data Collection |  | Once | 1 |  |  | 60 |  | 0 | 0 | 60 | 60 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1
Product Master | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Each | 1 | 30 | 30 | 30 |  | 30 | 30 | 30 | 90 | 0.5 | 0.5 | 0.5 | 1.5 | 1 | 1 | 1 | 3
Product Object | SB populates DPWB | Product | 1 |  |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product Object | SB reviews data from client | Product | 5 |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bundle Master | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Each | 1 | 60 | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bundle overhead |  | Bundle | 1 |  | 60 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product Feature |  | Feature | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product Option |  | Option | 1 |  |  | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option Constraint Object |  | Constraint | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product Rule |  | Rule | 1 |  | 5 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Configuration Attribute |  | Attribute | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bundle assistance | SB assists customer | Bundle | 1 | 15 | 60 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Guided Selling | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Each | 1 | 60 | 60 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quote Process |  | Process | 1 |  | 5 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process Input |  | Input | 1 |  | 5 | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Action | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Each | 1 |  | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Action |  | Action | 1 |  | 5 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Search Filters |  | Filter | 1 |  | 5 | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pricing Engine | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop | Mandatory to explain at least pricing structure | Each | 1 | 60 | 60 | 60 |  | 60 | 60 | 60 | 180 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3
Discount Schedule |  | Schedule | 1 |  | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Discount Tier |  | Tier | 1 |  |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block Prices |  | Tier | 1 |  |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Price Rule |  | Rule | 1 |  | 10 | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracted Prices |  | Contracted Price | 1 |  |  | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Price Books |  | Batch | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Multi-Dimensional Quoting |  | Price Dimension | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDQ Workshop |  | Once | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CSV Import Formats |  | Import Format | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output Documents | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Template | 1 | 60 | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead per template | Template setup, including basic grouping (e.g. Family) | Template | 1 |  | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead per page | Complexity factor - Average buffer per page | Page | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strict branding guidelines | Complexity factor - Average buffer per page | Page | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rich graphics | Complexity factor - Average buffer per page | Page | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line Columns |  | Column | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sections (including template content) |  | Section | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T&Cs - Static with merge fields |  | Page | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T&Cs - Static text - Column Formatting | Overhead of column formatting | Page | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
Quote Term | Assumes up to 1 condition per term on average | Term | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Grouping |  | Yes/No | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Rollup |  | Yes/No | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conditional Sections |  | Number | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conditional Column |  | Number | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filtered line items |  | Section | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e-Signature | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
DocuSign |  | Yes/No | 1 |  |  | 240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EchoSign |  | Yes/No | 1 |  |  | 120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fields to capture | Number of tags to define in the template content | Field | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Native SFDC Approvals | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Once | 1 | 60 | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Auto-Approval Process | Includes standard entry/final actions | Yes/No | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approval Process | Includes standard entry/final actions | Process | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Single Reason Step | Number of tiers/thresholds | Step/Tier | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Step (multi-reason) | Includes creation of flags for logic | Step/Tier | 1 |  | 15 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Email Template (HTML) | Typically 4 templates | Template | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advanced Approvals | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshops |  | Once | 1 | 240 | 240 | 240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approval Rules |  | Rule | 1 |  | 15 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approval Chains |  | Chain | 1 |  | 30 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approvers |  | Approver | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Email Templates | Typically 4 templates | Template | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Parallelism |  | Yes/No | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Renewals | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Standard renewals |  | Once | 1 |  |  | 240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract Amendment Workshop |  | Once | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UAT | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Status Calls | Typically: one 30-min call per day | Week | 1 | 150 | 150 | 150 |  | 150 | 150 | 150 | 450 | 2.5 | 2.5 | 2.5 | 7.5 | 3 | 3 | 3 | 9
Consultant assistance | 20% of Consultant Build Time | Hours | 1 |  |  | 20% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Architect assistance | 10% of Architect Design Time | Hours | 1 |  | 10% |  |  |  | 9 |  | 9 | 0 | 0.15 | 0 | 0.15 | 0 | 1 | 0 | 1
Admin Orientation | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Bundles | Only those implemented by SB | Bundle | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pricing |  | Price Rule | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approvals |  | Process | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advanced Approvals |  | Once | 1 |  |  | 120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Document Output |  | Template | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deployment | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Meta-data migration |  | Each | 1 |  |  | 120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Partial data migration | Excludes products and bundles | Each | 1 |  |  | 240 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Full data migration |  | Each | 1 |  |  | 720 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manual steps |  | Each | 1 |  |  | 120 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Migration Tool License |  | Yes/No | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Post Go Live Support | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Support | 8 hours per 100 hours of build | Hours | 12.5 | 30 | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aggregates | [7 empty] | PM | Architect | Consultant | Total | PM | Architect | Consultant | Total | PM | Architect | Consultant | Total
Pre-Build Activities | Except workshops | [6 empty] | 1140 | 337.5 | 645 | 2122.5 | 19 | 5.625 | 10.75 | 35.375 | 19 | 7 | 12 | 38
Workshops | [7 empty] | 90 | 90 | 90 | 270 | 1.5 | 1.5 | 1.5 | 4.5 | 2 | 2 | 2 | 6
Build Activities | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Post Build Activities | [7 empty] | 150 | 159 | 150 | 459 | 2.5 | 2.65 | 2.5 | 7.65 | 3 | 4 | 3 | 10
Total Activities | [7 empty] | 1380 | 586.5 | 885 | 2851.5 | 23 | 9.775 | 14.75 | 47.525 | 24 | 13 | 17 | 54
Verify with Total Project | [7 empty] | 1380 | 586.5 | 885 | 2851.5 | 23 | 9.775 | 14.75 | 47.525 | 24 | 13 | 17 | 54
Build duration in weeks | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Migration Duration | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project duration in Weeks | [7 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
PM Oversight Activities | [7 empty] | 900 | 157.5 | 135 | 1192.5 | 15 | 2.625 | 2.25 | 19.875 | 15 | 4 | 3 | 22
Document Templates
Number of templates | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Number of pages | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template 1 | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Template | 1 | 60 | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead per template |  | Template | 1 |  | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead per page |  | Page | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strict branding guidelines |  | Page | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rich graphics |  | Page | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line Columns |  | Column | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sections (including template content) |  | Section | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T&Cs - Static with merge fields |  | Page | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T&Cs - Static text - Column Formatting | Overhead of column formatting | Page | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quote Term |  | Term | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Grouping |  | Yes/No | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Rollup |  | Yes/No | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conditional Sections |  | Number | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conditional Column |  | Number | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filtered line items |  | Section | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Template 2 | Notes | UOM | Divider | PM | Architect | Consultant | Comments (if override)
Workshop |  | Template | 1 | 60 | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead per template |  | Template | 1 |  | 60 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead per page |  | Page | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strict branding guidelines |  | Page | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rich graphics |  | Page | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Line Columns |  | Column | 1 |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sections (including template content) |  | Section | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T&Cs - Static with merge fields |  | Page | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T&Cs - Static text - Column Formatting | Overhead of column formatting | Page | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quote Term |  | Term | 1 |  |  | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Grouping |  | Yes/No | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Custom Rollup |  | Yes/No | 1 |  | 15 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conditional Sections |  | Number | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Conditional Column |  | Number | 1 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Filtered line items |  | Section | 1 |  |  | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D5: Gilles: Use a divider other than 1 to impact the time allocated for the activity. Examples: 1) Steering Committee is supposed to occur every other week. Divider = 2 2) Review product tab in the Data Prep Work Book taking 1 minute per 5 rows (i.e. per 5 products) in the spreadsheet. Divider = 5
Note on D11: Gilles: Converts assumed time to once every other week.
Note on D32: Gilles: Review 5 products in the time allocated (1 minute)

## Estimate
SteelBrick CPQ - Scoping Estimate
Implementation Rates
Client | ACME Company |  |  |  | 225 | PM Rate
Project Type | First Implementation |  |  |  | 225 | Architect Rate
Salesforce Edition | Enterprise |  |  |  | 225 | Consultant Rate
SB CPQ Licenses | 10 |  |  |  | 225 | Buffer Rate
Total ACV | 10000
Total Services | 12375 |  |  |  |  | Customization Rates
Attach Ratio | 1.2375 |  |  |  | 250 | PM Rate
[5 empty] | 250 | Architect Rate
[5 empty] | 250 | Consultant Rate
Calculated Project Duration | 3 |  |  |  | 250 | Buffer Rate
Recommended Range for Project Duration | 1 | 5
Justify Project Duration Discrepancy
Calculated PM Hours per Week | 8
Recommended Minimum PM Hours per Week | 2
Justify PM Hours Discrepancy
Category | PM | Architect | Consultant | Buffer/Risk Factor | Total | Comments
Project Management | 19 | 7 | 6 |  | 32
Installation and Setup | 0 | 0 | 2 |  | 2
Product Catalog | 1 | 1 | 5 |  | 7
Bundles | 0 | 0 | 0 |  | 0
Guided Selling & Custom Actions | 0 | 0 | 0 |  | 0
Pricing and Discounting | 1 | 1 | 2 |  | 4
Output Documents | 0 | 0 | 0 |  | 0
Electronic Signature | 0 | 0 | 0 |  | 0
Approvals | 0 | 0 | 0 |  | 0
Renewals | 0 | 0 | 0 |  | 0
User Acceptance Testing | 3 | 4 | 3 |  | 10
Admin Orientation | 0 | 0 | 0 |  | 0
Deployment | 0 | 0 | 0 |  | 0
Post Go-Live Support | 0 | 0 | 0 |  | 0
Documentation |  |  |  |  | 0
0
0
0
0
0
Total Hours | 24 | 13 | 18 | 0 | 55
Total PS Fees | 5400 | 2925 | 4050 | 0 | 12375
Average per week (Total) | 8 | 4.3333 | 6 |  | 18.3333
Average per week (Build) | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0!
Average per week (PM oversight only) | 5 | 1.3333 | 1 |  | 7.3333
Customizations | PM | Architect | Developer | Buffer | Total | Comments
0
0
0
0
Total Hours | 0 | 0 | 0 | 0 | 0
Total PS Fees | 0 | 0 | 0 | 0 | 0
Grand Total | 5400 |  | 4050 | 0 | 12375

## Version History
Version Number | Changes | Approved By | Approval Date | Future Enhancements | Requested By | Planned Version | Actual Version
3 | First GA Release | Gilles Muys | 2015-06-30 | Support for CSV Import into quote lines | Gilles | 4.2 | 4.2
4 | - Added MDQ - Added price books uploads - Added contract amendments - Added rate card - Added migration tool - Possibility to change time assumptions for each output doc - Added Excel comments for Divider numbers in Details |  |  | Ask number of resources. Plan 3 hours per week of PM activities for resources above 1. This replaces current calculations on lines 9 and 11 in the Details tab. Gilles: did not implement additional PM hours based on number of resources in v4.2, since we have more recent requirements associated with project type (impact of Enterprise projects) | Slava | 4.2
4.1 | - Tweaked calculation of project duration - Added Documentation line in Estimate tab |  |  | Ask "Is this an enterprise project". If yes, add more PM hours. Drives the minimum number of hours (5 for SMB, 16 for ENT). Add increment based on build hours: 1 additional PM hour/week for every 25 design + build hours. | Slava | 4.2 | 4.2
4.2 | - Support for CSV Import Formats - Added question for project type (EE/MM) - Added control over project duration in Estimate tab + Justification - Added control over PM Hours in Estimate tab + Justification - Added validation of duration for Orientation/UAT/Post Go Live for Enterprise projects - PM hours automatically increased (1 hour/25 hours of build) for Enterprise projects - Added question for number of resources for the build. Impacts calculated project duration. | Gilles Muys | 2015-10-30 | ENT projects: 12 weeks minimum - Orientation is at least 3 weeks - UAT is at least 3 weeks - Post Go Live is at least 1 week | Slava | 4.2 | 4.2
4.3 | - Added hand-off from SOW Owner to Project Team in Details tab. Impact on PM activities. - Corrected formulas of PM-related activities for Consultant so that they now take into account the number of resources entered in the Questionaire |  |  | Calculate estimate separately for prior purchase constraints (need to create more summary variables) | Gilles
5 | - Removed question about multi-level configuration (nested bundles) - Change the logic for features and options for bundles. It's now expecting the total number of objects to create, instead of an average per bundle. - Changed the questions about product catalog, so that we clearly specify how many we setup and how many we review (instead of working by difference between the 2 numbers). |  |  | Email 10/18/2015 from Slava to Services: Total hours without PM a. <100 hours -> 2 hrs/wk (except enablement) a. 100-200 -> 5 hrs/wk b. 200-300 -> 8 hrs/wk c. 300-500 -> 10 hrs/wk d. 500-800 -> 15 hrs/wk e. 800-1100 -> 20 hrs/wk f. 1100-1500 -> 25 hrs/wk g. 1500+ -> 30 hrs/wk Also, please ensure that are adjusting the duration of the project accordingly. If it is an enterprise client, it is unlikely that they will be able to move really fast through the implementation so we need to account for this. In addition to this, the total number of week in a project should be a sliding scale as well: a. <100 hrs -> 1-5 wks a. 100-200 -> 5-8wks b. 200-300 -> 5-8wks c. 300-500 -> 10-12 wks d. 500-800 -> 12-14 wks e. 800-1100 -> 14-16 wks f. 1100-1500 -> 16-20 g. 1500+ -> 18-20 wks (add resources as needed) | Slava | 4.2 | 4.2
Tweak warning on Custom Actions, so that only one of the 2 types of filters is required, instead of both being required.

## Utilities (hidden)
Deployment Type | Project Duration Check |  |  | a. <100 hrs -> 1-5 wks a. 100-200 -> 5-8wks b. 200-300 -> 5-8wks c. 300-500 -> 10-12 wks d. 500-800 -> 12-14 wks e. 800-1100 -> 14-16 wks f. 1100-1500 -> 16-20 g. 1500+ -> 18-20 wks (add resources as needed)
None | Project Hours | Min Weeks | Max Weeks
Partial | 0 | 1 | 5
Full | 100 | 1 | 5
| 200 | 5 | 8
| 300 | 5 | 8
Boolean Flag | 500 | 10 | 12
TRUE | 800 | 12 | 14
FALSE | 1100 | 14 | 16
| 1500 | 16 | 20
| 9999999 | 18 | 20
Project Type
Enterprise
Mid Market | PM Hours Check
| Non PM Hours | Min Hrs/Week
| 0 | 2
| 100 | 2
| 200 | 5
| 300 | 8
| 500 | 10
| 800 | 15
| 1100 | 20
| 1500 | 25
| 9999999 | 30